## Instructions
		Using the Status tracker

At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
	If 5 team members each spent an hour, that counts as 5 hours
	Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)

For new activities, identify the type of activity - documentation, coordination, estimation etc.

At the end of each week, plan ahead for the following week
	Identify people responsible for each activity
	Estimate the hours needed for the activity

TEAM NAME	Team 39
PROJECT NAME	Word Sense Disambiguation in Crowd Sourcing Mode
PROJECT MENTOR	Prof .Vineet Chaitanya , Prof Dipti Misra Sharma ,Sukhada Sharma
TEAM MEMBERS	Nazrul Haque Athar
	Anubhav Srivastava
	Ankit Kotak
	Abhinav Pandey
	Jayanth Katuri

## Team_Status
TEAM NAME	Team 39
PROJECT NAME	Word Sense Disambiguation in Crowd Sourcing Mode
PROJECT MENTOR	Prof .Vineet Chaitanya , Prof Dipti Misra Sharma ,Sukhada Sharma

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %

Week 6 (sept 5- sept 11)
Learn Eclipse	Preparation	Nazrul	6	5.5	Done	Using IDEs can make our job easier	0.5	9.0909090909
Role preferences	Coordination	Anubhav	1.25	1.92	Done		-0.67	34.8958333333
SVN Repository setup	Preparation	Ankit	1.65	2.58	Done		-0.93	36.0465116279
Discuss bug report software	Preparation	Abhinav	2.5	2.5	Done	Redmine has been decided as the bug reporting software	0	0
Develop questions for requirements elicitation	Documentation	Jayanth	3.75	3.35	Done	Scoping Questions have been included	0.4	11.9402985075
Get account and configure website	Preparation	Ankit	1.25	1.25	Done	Registered and Checked	0	0
Research existing technology	Preparation	Jayanth	2.1	1.65	Done		0.45	27.2727272727
Project synopsis writeup	Documentation	Nazrul	2.5	3.35	Done		-0.85	25.3731343284
Identify role owners	Preparation	Anubhav	1.25	1.65	Done	Roles Allocated	-0.4	24.2424242424
Team Meeting	Coordination	Nazrul	5	5	Done	Team Meetings have started.	0	0
Status tracker	Documentation	Abhinav	2.5	3.75	Done	Tracking	-1.25	33.3333333333
Week 7 (sept 12 - sept 18)
Deciding Technoligies	Preparation	Abhinav	2.5	2.5	Done	Deciding Technology to be used for both Desktop and Application.	0	0
Project Status Report	Documentation	Anubhav	1.65	1.25	Done		0.4	32
Team Meeting	Coordination	Nazrul	5	5	Done	Deciding on Technologies .	0	0
Research existing technology	Preparation	Ankit	2.1	1.65	Ongoing		0.45	27.2727272727
Develop Questions to be asked to the Client	Documentation	Jayanth	2.5	2.1	Done		0.4	19.0476190476

Week 8 (sept 19 - sept 25)
Interface dicussion	Requirements	Nazrul	1.2	1.4	Done		-0.2	14.2857142857
Learning web2py	Preparation	Ankit	15	16	Ongoing		-1	6.25
Team Meeting	Coordination	Nazrul	5	5	Done	Deciding on Technologies .	0	0
Research existing technology	Preparation	Abhinav	2.5	2.5	Done		0	0
Project Status Report	Documentation	Anubhav	1.66	1.58	Done		0.08	5.0632911392
Deciding Technoligies for Desktop application	Preparation	Jayanth	5	5	Ongoing		0	0
Week 9
Interface dicussion	Requirements	Nazrul	12	12.5	Done		-0.5	4
Desktop Application:Research	Preparation	Ankit	13	14	Done		-1	7.1428571429
Team Meeting	Coordination	Nazrul	5	5	Delayed	Client not available	0	0
Explore Stanford Anusaarka Software	Preparation	Abhinav	9	9.5	Ongoing		-0.5	5.2631578947
Project Status Report	Documentation	Anubhav	10	10	Done		0	0

Week 10
Web Interface Approval	Requirements	Nazrul	1.4	1.5	Done		-0.1	6.6666666667
Desktop Application : Technology	Preparation	Jayanth	5	5	Done
Team Meeting	Coordination	Nazrul	2.5	3.25	Done
Making changes in Anusaaraka Software	Development	Abhinav	5	8.15	Delayed		-3.15	38.6503067485
Project Status Report	Documentation	Anubhav	9	9.5	Done		-0.5	5.2631578947
Week 12

Week 13

Week 14

Week 15

Week 16

Week 17

## Individual_Status
TEAM NAME	Team 39
PROJECT NAME	Word Sense Disambiguation in Crowd Sourcing Mode
PROJECT MENTOR	Prof .Vineet Chaitanya , Prof Dipti Misra Sharma ,Sukhada Sharma

Actvities	Nazrul Haque Athar		Anubhav Srivastava		Ankit Kotak		Abhinav Pandey		Jayanth Katuri		Estimated Total Hours	Actual Total Hours
	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent
Week 6 (sept 5- sept 11)
Learn Eclipse	0	0	0	0	0	0	0	0	0
Role preferences	0.25	0.33	0.25	0.42	0.25	0.42	0.25	0.33	0.25	0.42	1.25	1.92
SVN Repository setup	0.33	0.5	0.33	0.5	0.33	0.58	0.33	0.5	0.33	0.5	1.65	2.58
Discuss bug report software	0.5	0.5	0.5	0.5	0.5	0.5	0.5	0.5	2.5	2.5
Develop questions for requirements elicitation	0.75	0.67	0.75	0.67	0.75	0.67	0.75	0.67	0.75	0.67	3.75	3.35
Get account and configure website	0.25	0.25	0.25	0.25	0.25	0.25	0.25	0.25	1.25	1.25
Research existing technology	0.42	0.33	0.42	0.33	0.42	0.33	0.42	0.33	0.42	0.33	2.1	1.65
Project synopsis writeup	0.5	0.67	0.5	0.67	0.5	0.67	0.5	0.67	0.5	0.67	2.5	3.35
Identify role owners	0.25	0.33	0.25	0.33	0.25	0.33	0.25	0.33	0.25	0.33	1.25	1.65
Team Meeting	1	1	1	1	1	1	1	1	5	5
Status tracker	0.5	0.75	0.5	0.75	0.5	0.75	0.5	0.75	0.5	0.75	2.5	3.75
Week 7 (sept 12 - sept 18)
Deciding Technoligies	0.5	0.33	0.5	0.42	0.5	0.5	0.5	0.75	0.5	0.5	2.5	2.5
Project Status Report	0.33	0.25	0.33	0.25	0.33	0.25	0.33	0.25	0.33	0.25	1.65	1.25
Team Meeting	1	1	1	1	1	1	1	1	5	5
Research existing technology	0.42	0.33	0.42	0.33	0.42	0.33	0.42	0.33	0.42	0.33	2.1	1.65
Develop Questions to be asked to the Client	0.5	0.42	0.5	0.42	0.5	0.42	0.5	0.42	0.5	0.42	2.5	2.1
0						0	0
Week 8 (sept 19 - sept 25)
Interface discussion	0.2	0.2	0.2	0.3	0.3	0.4	0.2	0.2	0.3	0.3	1.2	1.4
Learning web2py	2	2	3	3	5	6	3	3	2	2	15	16
Team Meeting	1	1	1	1	1	1	1	1	5	5
Research existing technology	0.5	0.5	0.5	0.5	0.5	0.5	0.5	0.5	2.5	2.5
Project Status Report	0.33	0.25	0.33	0.33	0.3	0.3	0.4	0.4	0.3	0.3	1.66	1.58
Deciding Technoligies for Desktop application	1	1	1	1	1	1	1	1	5	5
Week 9						0	0
Interface discussion	1	1	2	1.5	3	4	4	3	2	3	12	12.5
Desktop Application:Research	1	2	2	2	3	3	4	4	3	3	13	14
Team Meeting	1	1	1	1	1	1	1	1	5	5
Explore Stanford Anusaarka Software	1.5	1.5	2	2	1.5	2	2	2	2	2	9	9.5
Project Status Report	2.5	2.5	2	2	1.5	1.5	2	2	2	2	10	10
Week 10						0	0
Web Interface Approval	0.2	0.2	0.2	0.3	0.3	0.3	0.4	0.4	0.3	0.3	1.4	1.5
Desktop Application : Technology	1	1.5	1	1.5	1	1.5	1	1.5	1	1.5	5	7.5
Team Meeting	1	1	1	1	1	1	1	1	5	5
Making changes in Anusaaraka Software	1	1.5	1	1.5	1	2	1	1.75	1	1.4	5	8.15
Project Status Report	1.5	1.5	2	2.5	1.5	1.5	2	2	2	2	9	9.5
Week 12						0	0
0						0	0
0						0	0
0						0	0
0						0	0
Week 13						0	0
0						0	0
0						0	0
0						0	0
0						0	0
Week 14						0	0
0						0	0
0						0	0
0						0	0
0						0	0
Week 15						0	0
0						0	0
0						0	0
0						0	0
Week 16						0	0
0						0	0
0						0	0
0						0	0
0						0	0
Week 17						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0